## Plan
Month | Phase | Objective | Detailed Implementation | Deliverables | Weekly Status of the Features | Responsibility | Functional Features | Non-Functional Features | Remarks
March | Phase 1 (Start) – System Foundation | Define system boundaries, architecture, and flow | Finalize architecture (microservices-based); define borrower to lender workflow; identify modules; initialize GitHub structure | Architecture draft; flow definition; repo structure | Week 1: Understood problem scope, finalized core modules (ingestion, features, scoring, explainability, fraud). Week 2: Defined borrower to lender flow and mapped how data moves across modules; aligned demo flow with system logic. Week 3: Drafted initial architecture (layer-wise); started defining data schema (bank, EPFO, utility features). Week 4: Initialized GitHub structure; identified what components are real vs simulated; refined architecture based on feedback. | Hazel: architecture setup; Freia: flow + schema draft | Basic borrower flow; module identification | Modular design; clarity of system boundaries | Initial setup done.
April | Phase 1 (Complete) – System Foundation | Finalize architecture and compliance flow | Define API contracts (input/output schema); finalize data schema (bank, EPFO, utilities); define consent lifecycle; identify mocked vs real components | Architecture doc; API design; data schema doc; updated repo | Week 1: Refined data schema for bank, EPFO, and utility features; clearly define what inputs and derived features the system will use. Week 2: Define API flow and basic endpoints (upload, feature extraction, scoring, explanation); mapped how modules will interact. Week 3: Start building a basic pipeline using sample/dummy data; simulated input to feature extraction flow. Week 4: Consolidate architecture, API design, and data schema into proper documentation; cleaned up GitHub structure and align everything for next phase. | Hazel: API + backend design; Freia: data schema + consent | Borrower data intake; consent capture; API structure | Data minimization; compliance alignment (DPDPA); scalable design | Main focus month. We plan to properly document everything and make the system flow very clear.
May (1st Half) | Phase 2 (Start) – Data Pipeline | Begin data extraction and feature planning | Research PDF parsing; test basic extraction (bank/salary); define feature engineering logic | Initial parsing scripts; feature list | Week 1: Research PDF parsing approaches for bank statements and salary slips; identify required fields for extraction; align extracted fields with the defined feature schema. Week 2: Start implementing basic parsing scripts for document input; test extraction of key fields; begin mapping extracted data to feature engineering logic. | Freia: parsing + features; Hazel: integration planning | Data ingestion (basic); feature definition | Accuracy awareness; structured pipeline planning | College exams scheduled from 6th May to 12th May, so the focus during this period will be on research, testing approaches, and gradual implementation planning.
May (2nd Half) | Phase 2 (Build) – Data Pipeline | Implement structured extraction and features | Build parsers; extract structured data; implement feature calculations (cashflow, utilities, EPFO); add validation checks | Working extraction scripts; feature outputs | Week 3: Generate synthetic borrower datasets for different financial profiles; define validation rules for extracted financial data; map behavioural features to the PRISM feature schema. Week 4: Implement feature engineering calculations using synthetic datasets; test validation checks and risk interpretation logic; generate structured outputs for downstream scoring integration. | Freia: core implementation; Hazel: backend linking | Feature extraction; data validation | Data privacy (no raw storage); logging; fault tolerance | Start of vacation period, so we expect good progress here.
June | Phase 2 (Complete) – Data Pipeline | Stabilize feature pipeline | Refine feature engineering; generate clean datasets; validate outputs; ensure PII is not stored | Clean datasets (CSV/JSON); validation logs | Week 1: Refine synthetic datasets and feature definitions; standardize output formats across bank, salary, and utility document pipelines. Week 2: Begin testing extraction outputs with parser modules; validate extracted fields and map them to structured feature generation workflows. Week 3: Integrate feature extraction outputs with backend APIs; implement logging and error-handling for extraction and validation stages. Week 4: Perform end-to-end testing of extraction, validation, and feature generation pipeline; generate clean datasets, validation logs, and pipeline documentation. | Freia: pipeline owner; Hazel: integration | Multi-source data handling; structured outputs | Pipeline efficiency; consistency; secure handling | One of the main technical phases. We’ll focus on getting this stable before moving ahead.
July | Phase 3 – Scoring & Sentiment | Build scoring logic and behaviour signals | Implement rule-based scoring (weighted features); define scoring formula; build basic NLP (keyword/TF-IDF); generate score, tier, confidence | Scoring engine; output samples | Week 1: Implement mobile number-based login and OTP verification; replace temporary session IDs and integrate user authentication with the database. Week 2: Refine the Logistic Regression scoring pipeline by validating WoE transformations, Probability of Default calculation, risk tiers, and confidence scoring. Week 3: Validate parser outputs using real-world datasets; compare extracted information with manual verification and refine feature mappings. Week 4: Integrate authentication, parser, scoring engine, and PostgreSQL; perform end-to-end testing, document limitations, and prepare the system for production-oriented deployment. | Hazel: scoring; Freia: NLP + mapping | Risk score; sentiment classification; risk tiers | Interpretability; stability; low compute complexity | We’ll try to complete most of scoring here.
August | Phase 4 – Explainability | Make scoring transparent | Implement rule-based explanations; generate reason codes; basic what-if logic; connect explanation to UI/API | Explanation outputs; API endpoints; UI integration |  | Freia: explainability; Hazel: API integration | Reason codes; feature contribution display | Auditability; clarity; regulatory alignment | This phase builds on scoring, so depends on previous phase stability.
September | Phase 5 – Fraud & Document Checks | Add fraud and document signals | Implement loan stacking detection (hashed identity); basic OCR parsing; metadata checks; anomaly detection logic | Fraud flags; document logs |  | Hazel: fraud logic; Freia: document pipeline | Fraud detection; document validation | Security; false-positive control; privacy (hashed IDs) | Might take some iteration as fraud logic is not straightforward.
October | Phase 6 – Integration | Connect full system | Integrate ingestion,features, scoring, explainability, fraud; build API flow; test end-to-end | Integrated system; working demo |  | Both | End-to-end workflow; unified output | API stability; latency optimization; reliability | Important milestone. Focus will be on making everything work together properly.
November | Phase 7 (Start) – Testing | Validate system outputs | Run system on public + synthetic datasets; evaluate scoring consistency and fraud signals | Initial validation results |  | Both | Output validation; performance checks | Robustness; consistency | Testing phase may need multiple iterations depending on results.
December | Phase 7 (Complete) – Finalization | Final validation and documentation | Benchmark vs traditional scoring; finalize reports; documentation; prepare final demo | Final report; complete demo |  | Both | Final system outputs; reporting | Documentation quality; reproducibility | Final polishing and cleanup phase before submission.

## Features
Category | Feature | Description | Output
Core Scoring | Multi-modal credit scoring | Combines bank, EPFO, utility data | Risk score (300–900)
| Risk tier classification | Categorizes borrower risk | Low / Medium / High
| Confidence score | Indicates reliability of output | Confidence band
Behavioural Analysis | Cashflow stability | Tracks income regularity | Stability metric
| Utility discipline | Measures bill payment consistency | Payment ratio
| Employment continuity | Uses EPFO history | Employment duration
NLP Module | Loan purpose classification | Classifies intent | Productive / Risky
| Sentiment scoring | Adds behavioural context | Risk modifier
Explainability | Reason codes | Explains score factors | Feature contributions
| What-if analysis | Simulates changes | Hypothetical outputs
Fraud Detection | Loan stacking detection | Detects multiple applications | Risk flag
| Identity anomaly detection | Flags unusual behaviour | Alert signals
Document Verification | OCR validation | Extracts & verifies fields | Structured data
| Metadata checks | Detects inconsistencies | Validation flags
| ELA analysis | Detects tampering | Authenticity score
Compliance Layer | Consent handling | Tracks user permission | Consent logs
| Data masking | Protects PII | Hashed identifiers
System Layer | API integration | Backend communication | JSON responses
| Dashboard | Borrower + lender UI | Visual outputs

## Reusable assets
Asset Type | What You Provide | Description | Reusability Value
Codebase | Backend modules | Scoring, fraud, explainability, APIs | Can be reused by fintech teams
| Frontend dashboard | Borrower & lender UI | Demo + extension ready
Data Pipeline | Feature extraction scripts | Bank, EPFO, utility parsing | Reusable for other fintech models
| Synthetic data generator | Generates test datasets | Useful for future testing
Datasets | Sample datasets | Public + synthetic structured data | Benchmarking & testing
| Processed feature datasets | Clean model-ready data | Model training reuse
Documentation | Architecture document | System design & flow | Reference for scaling
| API documentation | Endpoint definitions | Integration ready
| Data schema | Feature definitions | Standardization
Validation Reports | Performance reports | Accuracy, explainability analysis | Benchmark reference
| Comparison study | PRISM vs traditional scoring | Research value
Compliance Artifacts | Consent flow design | Data governance model | Regulatory reference
| Security design notes | Encryption, hashing logic | Implementation guide
Deployment Setup | Docker configs / setup files | Environment setup | Easy deployment
| GitHub repository | Full project code | Version-controlled reuse

## Feature Extraction
Data Source | Raw Input Field | Derived Feature Name | Description | Calculation / Logic | Type | Expected Impact on Risk
Bank Statements | Monthly balance | avg_balance | Average account balance over a period | Mean(balance over last N months) | Numerical | Higher means Lower risk
| Salary credits | income_consistency | Stability of income inflow | Std deviation / variance of monthly inflow | Numerical | Higher stability means Lower risk
| Total credits/debits | cashflow_ratio | Ratio of inflow vs outflow | Total credits / total debits | Numerical | Balanced means Lower risk
| Transaction history | transaction_volatility | Variation in transaction values | Std deviation of transaction amounts | Numerical | Higher volatility means Higher risk
| No. of transactions | activity_level | Frequency of account usage | Count of transactions per month | Numerical | Moderate means Healthy behaviour
| Minimum balance breaches | low_balance_flag | Indicates frequent low balance | Count of times balance < threshold | Binary / Count | More breaches means Higher risk
| EMI/loan debits | existing_obligation_ratio | Existing financial burden | EMI payments / total income | Numerical | Higher means Higher risk
| Overdraft / penalties | penalty_flag | Indicates financial stress | Presence of penalties/charges | Binary | Present means Higher risk
EPFO (Employment Data) | Employment history | employment_months | Total duration of employment | Months between joining and current date | Numerical | Higher means Lower risk
| Employer changes | job_switch_frequency | Frequency of job changes | No. of job switches / time period | Numerical | Higher means Higher risk
| Contribution pattern | epfo_consistency | Regularity of EPFO contributions | Consistency in monthly contributions | Numerical | Higher means Lower risk
| Missing contributions | employment_gap_flag | Indicates employment gaps | Gap in contribution timeline | Binary | Present means Higher risk
Utility Payments | Bill payments | utility_payment_consistency | Regularity of bill payments | No. of on-time payments / total bills | Numerical | Higher means Lower risk
| Missed payments | missed_payment_count | Number of missed bills | Count of unpaid/delayed bills | Numerical | Higher means Higher risk
| Payment delay | avg_payment_delay | Average delay in bill payment | Avg(days delayed) | Numerical | Higher means Higher risk
| Bill amount trend | utility_spend_stability | Stability in monthly utility spending | Std deviation of bill amounts | Numerical | Stable means Lower risk
Combined Behavioural Features | Income vs expenses | savings_ratio | Ability to save money | (Income − Expenses) / Income | Numerical | Higher means Lower risk
| Income vs obligations | repayment_capacity | Ability to repay loans | Income / existing obligations | Numerical | Higher means Lower risk
| Financial discipline | discipline_score | Composite behavioural score | Weighted combination of utility + bank features | Numerical | Higher means Lower risk